## Sheet1
Sample Lesson Study Timeline and Budget
for Elementary School
Lesson study is a long-term approach to continuous improvement of teaching and learning. This sample timeline and budget is based on actual school professional development plans that have led to significant changes in instruction across the school. The budget assumes that the cost per substitute is $225/day, and an hourly rate for after-school time of $90.
Budget Constants
| Substitute cost per day: | 225
| Hourly rate: | 90
Date & description | Subs | Grant cost | School cost | Comments
Sept 15: Selection of the school research committee. Introduction to Lesson Study by Knowledgeable Other (K.O.). Develop proposed school research theme. | 5 | 1125 |  | School research committee will include 4 lead teachers from K-5—2 ea. from K-2 & 3-5— and 1 from 5-8.
Date TBD: 4 teachers attend a public research lesson at either Prieto, Boone, Chavez, or O’Keeffe | 4 | 900 |  | (Actual dates/locations of public lessons should be known in September)
Oct 20: Grade level meetings: choose lesson focus, begin research. | 0 | 0 | 0
Oct 22: After-school meeting with K.O. to discuss lesson focus and the Common Core. |  |  | 720 | Hourly rate for teachers: $90/hr x 8 teachers x 1 hr.
Oct 28: Unit planning with K.O. | 4 | 900 | 100 | 3-5 in the a.m., K-2 in p.m. $100 honorarium to k.o. (if k.o. is a teacher, grant will pay for sub coverage)
Nov 4: K-2 and 3-5 teams develop draft research lesson plans | 4 | 900 |  | K-2 in a.m, 3-5 in p.m.
Nov 13 (p.d. day): 12 teachers from K-8 attend public research lessons at Prieto, Boone, or Chavez in order to experience Lesson Study. | 0 |  | 600 | $50/person registration fee (est.)
Nov 17: After-school meeting with k.o. for feedback on research lesson plan. |  |  | 720 | Hourly rate for teachers: $90/hr x 8 teachers x 1 hr.
Dec 1: K-2 lesson and discussion. | 10 | 2250 | 100 | Attendees: all 8 K-5 team members, 5-8 leadership team member, addit’l K-5 teacher, school principal, school assistant principal, network instructional support (invited). $500 honorarium for k.o.
Dec 2, after school: K-2 team + research committee: write newsletter for school faculty on findings from lesson and discussion; compile report for foundation. |  |  | 450 | Hourly rate for teachers: $90/hr x 5 teachers.
Jan 13: Grade 3-5 lesson and discussion | 10 | 2250 | 100 | Attendees: all 8 K-5 team members, 5-8 leadership team member, addit’l K-5 teacher, school principal, school assistant principal, network instructional support (invited). $500 honorarium for k.o.
Jan 14: 3-5 team + leadership team: write school newsletter on findings from lesson and discussion and submit to the foundation. | 7 | 1575 |  | Half-day only.
Feb 5 (p.d. day): 12 teachers from K-8 attend public research lessons at Prieto, Boone, or Chavez. |  |  | 600 | $50/person registration fee (estim.)
Mar 2: Grade K-2 team and 5-8 team research and begin developing unit plan with support from k.o. | 4 | 900 | 100 | K-2 in the a.m., 5-8 in p.m. $100 honorarium to k.o.
Mar 9: Gr 5-8 team & K-2 team develop research lesson plans | 4 | 900 |  | 5-8 in a.m., K-2 in p.m.
Mar 10, after school: feedback from k.o. |  |  | 720 | Hourly rate: $90 x 8 teachers x 1 hr
Mar 16, after school: 5-8 research lesson |  |  | 460 | Hourly rate for planning team: $90 x 4 teachers x 1 hr. Attendees: all teachers from school are invited, + school principal, school assistant principal, network instructional support (invited). $100 honorarium for k.o.
Mar 17 morning: K-2 research lesson in a.m.; afternoon: K-2 team, 5-8 team, research committee write school newsletter on findings from lesson and discussion and submit to the foundation | 10 | 2250 | 100 | Attendees: all 8 K-5 team members, 5-8 leadership team member, addit’l K-5 teacher, school principal, school assistant principal, network instructional support (invited). $100 honorarium for k.o.
May 5-6: Research committee attends Chicago Lesson Study Conference | 5 | 2250 | 1250 | Subs for 2 days; $250/person registration fee paid by the school
May 18: Research committee prepares final report: what was learned, what will be the direction of future work. Report is shared with school faculty and submitted to the foundation. | 5 | 1125
Stipends for teachers |  | 2240 |  | $140 x 4 teachers / team x 4 research lessons
TOTAL |  | 19565 | 6020