## Sheet1
Sample Lesson Study Timeline and Budget
for High School
Lesson study is a long-term approach to continuous improvement of teaching and learning. This sample timeline and budget is based on actual school professional development plans that have led to significant changes in instruction across the school.
Budget Constants
| Substitute cost per day: | 225
| Hourly rate: | 90
Date & description | Subs | Grant cost | School cost | Comments
Sept 15: Introduction to Lesson Study by Knowledgeable Other (K.O.). Develop proposed school research theme. | 5 | 1125
Date TBD: 4 teachers attend a public research lesson at either Prieto, Boone, Chavez, or O’Keeffe | 4 | 900 |  | (Actual dates/locations of public lessons should be known in September)
Oct 20: Grade level meetings: choose lesson focus, begin research.
Oct 22: After-school meeting with K.O. to discuss lesson focus and the Common Core. |  |  | 720 | Hourly rate for teachers: $90/hr x 8 teachers x 1 hr.
Oct 28: Unit planning with K.O. | 4 | 900 | 100 | algebra in the a.m., geometry team in p.m. $100 honorarium to k.o. (if k.o. is a teacher, grant will pay for sub coverage)
Nov 4: Algebra and geometry teams develop draft research lesson plans | 4 | 900 |  | geometry team in a.m, algebra in p.m.
Nov 13 (p.d. day): 8 teachers attend public research lessons at Prieto, Boone, or Chavez in order to experience Lesson Study. | 0 |  | 500 | $50/person registration fee (est.)
Nov 17: After-school meeting with k.o. for feedback on research lesson plan. |  |  | 720 | Hourly rate for teachers: $90/hr x 8 teachers x 1 hr.
Dec 1: Algebra lesson and discussion. | 10 | 2250 | 100 | Attendees: all 8 team members + 2 add'l teachers; school principal; school assistant principal; network instructional support (invited). $100 honorarium for k.o. (or grant can pay substitute coverage if k.o. is a teacher)
Dec 2, after school: Algebra team: write newsletter for math department on findings from lesson and discussion; compile report for foundation. |  |  | 450 | Hourly rate for teachers: $90/hr x 5 teachers.
Jan 13: Geometry lesson and discussion | 10 | 2250 | 100 | Attendees: all 8 team members + 2 add'l teachers; school principal; school assistant principal; network instructional support (invited). $100 honorarium for k.o.
Jan 14: Algebra team: write newsletter for math department on findings from lesson and discussion; compile report for foundation. | 4 | 900 |  | Half-day only.
Feb 5 (p.d. day): 8 teachers attend public research lessons at Prieto, Boone, or Chavez. |  |  | 200 | $50/person registration fee (estim.)
Mar 2: Geometry and Advanced Algebra teams research and begin developing unit plan with support from k.o. | 4 | 900 | 100 | Geometry in the a.m., AA in p.m.; $100 honorarium to k.o.
Mar 9: Geometry team & AA team develop research lesson plans | 4 | 900 |  | AA in a.m., Geometry in p.m.
Mar 10, after school: feedback from k.o. |  |  | 720 | Hourly rate: $90 x 8 teachers x 1 hr
Mar 16, after school: Advanced Algebra research lesson |  |  | 460 | Hourly rate for planning team: $90 x 4 teachers x 1 hr. Attendees: all teachers from department are invited, + school principal, school assistant principal, network instructional support (invited). $100 honorarium for k.o.
Mar 17 morning: Geometry research lesson and post-lesson discussion. | 10 | 2250 | 100 | Attendees: all 8 Geometry & AA team members + 2 add'l teachers, school principal, school assistant principal, network instructional support (invited). $100 honorarium for k.o.
afternoon: Geometry and AA teams write their findings from their lessons and discussions.
May 5-6: 2 memebers each from Algebra, Geometry, and AA teams attend Chicago Lesson Study Conference | 6 | 2700 | 1500 | subs for 2 days; $250/person registration fee paid by the school
May 18: Members of Geometry, Algebra, and AA teams write culminating reflection on learnings from the year and proposal for focus next year. | 6 | 1350
Stipends for teachers |  | 2240 |  | $140 x 4 teachers / team x 4 research lessons
TOTAL |  | 19565 | 5770